## Report
Execution Run Report — Buyer Approval Workflow
Project | Deliverables - Elevate Notion Document
Test Plan
Release
Environment | Microsoft Edge - Test Environment
Status | Completed
Progress | 4 / 4 executed
Created At | Jul 13, 2026 5:56 PM
Generated At | Jul 15, 2026 6:06 PM
Test Case | Status | Assigned To | Executed By | Executed At | Evidence | Actual Result
TC-DEL-012 — Check whether Project Approver is able to reject the approval task. | Pass | Sawan Kumar | Sawan Kumar | Jul 15, 2026 5:47 PM | Yes | Test Outcomes: 1. Validate whether approver is able to reject the approval task. Test Result - Yes, Approver is able to reject the approval task. 2. Test whether the new task is created and project status has been updated accordingly. Test Result - Project Request Rejection review task has been created, and project status has been updated as ' Buyer Approval Rejected'. 3. Validate whether the approval task status has been updated as 'Rejected' Test Result - Yes, updated as 'Rejected'
TC-DEL-011 — Test whether Project owner can be able to re-assign Approver task to self and complete the approval task. | Pass | Sawan Kumar | Sawan Kumar | Jul 15, 2026 5:35 PM | Yes | Testing Outcomes: 1. Validate whether project owner is able to re-assign the approval task to own from the project details page. Test Result: Project owner is able to re-assign the approval task to self. 2. Validate whether the current task assignee has been updated to Project Approver and previous assignee loss the right on the task. Test Result: Current task assignee has been added as a project approver and previous assignee not able to open the task. 3. Test whether while approving the approver task as a 'Project Owner', alert is showing for missing pre-approval task. Test Result: Alert is showing while approving the approval task from the Project Owner role. 4. Test whether task has been completed after uploading the pre-approval task. Test Result: Task has been successfully completed, and all task has been now marked as 'Completed'.
TC-DEL-013 — Validate once, Project Rejection Review Task has been completed, Previous Approval task has been again - In Progress | Pass | Sawan Kumar | Sawan Kumar | Jul 15, 2026 6:00 PM | Yes | Testing Outcomes: 1. Check whether Project request rejection review task has been assigned to primary project owner. Test Result - Yes, assigned to project owner. 2. Check whether project update changes are reflecting in the task. Test Result - Project changes are reflecting in the task. 3. Test whether project status has been updated to Buyer Approver and Approver task status will be updated from Rejected to In Progress. Test Result - Project status & task status has been updated as per the requirement. 4. Test whether the task has been sent to the primary test approver as per membership list. Test Result - Yes. 5. Test Whether task has been approved and all status has been updated accordingly. Test Result - Task has been approved and all status has been updated accordingly.
TC-DEL-010 — Validate whether approver task is created when approver is required in the created project. | Pass | Sawan Kumar | Sawan Kumar | Jul 15, 2026 5:00 PM | Yes | Approver task has been sent to the selected project approver, and the project approver is able to 'Approve' the project approval task. Task has been marked as 'Completed' Project status has been updated from Buyer Approver to 'Submitted & In Review' New Project draft group has been marked as 'Completed'.