CONTENTS

- PROJECT TITLE

- INTRODUCTION & BACKGROUND

- SCOPE OF THE CONTRACT

- DETAILED REQUIREMENTS

- MILESTONES

- CONTRACT MANAGEMENT

- DATA PROTECTION

- EVALUATION

NORTH EAST MAYORAL COMBINED AUTHORITY t/a/ NORTH EAST COMBINED AUTHORITY

- Project Title

Budget Mapping: Place Based Budgets for Prevention of Youth Offending in South Tyneside and Gateshead – Sawan Test Project

- Introduction & Background

The North East Mayoral Strategic Authority (MSA) was formed on 7 May 2024 and is led by an Elected Mayor and Cabinet and covers the seven local authority areas of County Durham, Gateshead, Newcastle, North Tyneside, Northumberland, South Tyneside and Sunderland.

The North East MSA’s purpose is to champion the full potential of our region. Collaborating with our partners and local authorities, we’ll create a better way of life by connecting communities, giving people the skills to succeed, and improving wellbeing for all, so that the North East is recognised as an outstanding place to live, work, visit and invest.

Investing in job creation, good work, and a skilled regional workforce lie at the heart of the North East Mayoral and Cabinet’s manifesto, prioritising:

- Home to a growing and vibrant economy for all

- Home of the green energy revolution

- A welcoming home to global trade

- Home of real opportunity

- A North East we are proud to call home

National Place Based Budget Pilot

The national Place Based Budget Pilot programme was officially launched by the Cabinet Office in March 2026. The North East is one of five Mayoral Strategic Authorities backed to deliver this landmark initiative in close partnership with the Ministry of Housing, Communities and Local Government and the Cabinet Office.

The North East pilot focuses on preventing youth offending for children and young people (up to age 25) across Gateshead and South Tyneside. It will test how integrated, crosscutting public spending can prevent youth offending upstream, reduce long term demand on acute services, improve life chances, and demonstrate public value through system redesign.

The pilot will test an ambitious multiagency, person centred, systemwide approach to prevention, using pooled budgets, integrated data, and shared accountability. The long-term objective is to reduce youth offending. The project will also set medium term, and short term aims that could include reduction in NEET (Not in Education, Employment or Training) rates, improving educational engagement, and strengthening emotional wellbeing of children and young people.

- Scope of the Contract

The Authority is seeking to appoint a suitably qualified SPS Provider to undertake a baseline financial mapping of current budgets across organisations and trace money system flows specifically for – though not limited to - the following opportunity areas identified below.

| Opportunity Area | Challenge | Potential System Areas / Budgets in Scope |
| --- | --- | --- |
| Belonging, Identity and Community | Young people can become disconnected from their communities and develop a sense of identity linked to offending, antisocial behaviour or exploitation. The commission should explore how public investment currently supports belonging, community connection and protective factors. | Community safety, youth provision, family hubs, neighbourhood services, public health, community development, Voluntary, Community and Social Enterprise (VCSE) provision, diversionary activities and place-based initiatives. |
| Family Adversity, Trauma and Instability | Many young people experiencing or at risk of offending are affected by poverty, trauma, instability and complex family circumstances. The commission should examine how resources are deployed across the system to respond to these needs and whether opportunities exist for earlier and more coordinated intervention. | Early help, children's social care, family support, family hubs, housing, substance misuse services, mental health services, youth justice and relevant VCSE provision. |
| School Exclusion, SEND and Education Engagement | Poor educational engagement, exclusion, absence and unmet additional needs can increase vulnerability to offending. The commission should identify how funding flows through the education and support system and where barriers, inefficiencies or opportunities for prevention exist. | Mainstream education, SEND services, alternative provision, inclusion services, attendance support, educational psychology, youth justice and commissioned education-based interventions. |
| Strengths, Aspirations and Resilience | Young people do not always have access to sustained opportunities, trusted relationships and positive pathways that build confidence, skills and aspirations. The commission should consider how current investment supports resilience, positive activities and long-term outcomes. | Youth services, sport and culture, employability programmes, mentoring, diversionary activities, VCSE provision, community organisations and wider family support services. |

For each of the opportunity areas outlined, the work will support partners in the following ways:

- Understand where the money sits.

- How the money moves through the system.

- Where money is lost in the system.

- Identify and make recommendations about where the system can shift structurally.

- Identify any barriers or blockers.

- Summarise and present these findings in a Report.

- Detailed Requirements

The commissioned SPS provider will be expected to deliver a comprehensive, system-wide baseline financial mapping across two local authorities and the police force and some light touch work across partner agencies. This is likely to include: reported spend on preventive activity such as alternative provision by schools and commissioned health activity (Integrated Care Board). Activities must include, but are not limited to, the following:

4.1. Budget Identification & Financial Mapping

Within the context of the four opportunity areas, the commissioned SPS Provider will:

- Identify and catalogue current budgets relevant to youth offending, prevention, early help, safeguarding, education, SEND, health, community safety and policing.

- Name each budget line explicitly, including budget holder; originating organisation; statutory or discretionary status; commissioning arrangements; and service eligibility criteria and charging approaches (where applicable).

- Map where funding currently sits across the system, including governance arrangements, decision-making structures and accountability.

- Analyse budget size, trends and utilisation, supported by available benchmarking or comparator data where appropriate.

This phase should provide a clear baseline of the financial landscape and support the mobilisation of stakeholder engagement across agencies.

4.2. Mapping System Flows & Spend Patterns

- Analyse and visually map how resource and activity flows through the system, including: referral pathways and thresholds; decision points and handover stages; commissioning flows and provider relationships; and interdependencies between agencies.

- Map spending flows alongside service pathways to show how funding supports (or fails to support) the end-to-end journey.

- Identify, where possible, the proportion of spend fits in primary, secondary or tertiary prevention model (Ref Chartered Institute of Public Finance and Accountability - CIPFA Prevention Spend Audit Toolkit).

This work should highlight key pressure points and enable integration of financial and operational insights within a detailed system map.

4.3. Identifying Value Leaks & Inefficiencies

- Identify areas where resource is lost, diluted or inefficiently used, including duplication of services or assessments; waiting times and delays; late identification of need; fragmented or misaligned commissioning; and escalation resulting from unmet need or system delay.

- Examine cross-agency impacts, including where savings or restrictions in one part of the system create additional demand or cost elsewhere; and inefficiencies at referral and handover points.

- Provide a clear narrative and visual representation of these value leaks, including flows between agencies and points of resource attrition.

4.4. Structural Opportunities for System Shift

- Using the analysis, identify opportunities to improve outcomes through more joined-up and preventative approaches, including:

  - pooled and/or aligned budgets

  - joint commissioning arrangements

  - shared outcomes frameworks and performance measures

  - integrated or streamlined pathways

  - improved data sharing and interoperability

  - upstream reinvestment and prevention models

- Develop and present a set of practical options and recommendations, including early investment opportunities and operational changes that improve system effectiveness for both budget holders and young people.

4.5 Barriers, Risks & Governance Considerations

- Identify barriers to cross-agency working and system change, including:

  - financial governance and accountability arrangements

  - statutory constraints

  - data limitations and incompatibility

  - organisational culture, incentives and misaligned objectives

- Set out risks associated with proposed changes and provide mitigation strategies.

- Propose solutions to overcome barriers, including governance models, shared standards, and delivery mechanisms (e.g. time-limited taskforces or pooled budget arrangements).

Service Activities

The commissioned SPS Provider will be expected to undertake the following core activity as part of their methodology.

4.6. Inception and Governance Engagement

- Attend an inception meeting to confirm scope, expectations, timelines, reporting requirements and data needs.

- Agree mobilisation arrangements, including administrative support for stakeholder identification, engagement and meeting coordination.

- Identify and engage all relevant organisations and budget holders across the system.

- Participate in regular check-ins with the Finance sub-group to: test emerging findings; validate assumptions; ensure alignment with system priorities.

- Provide clear updates on progress, risks and dependencies.

4.7 Desk-Based Research and Document Review

- Undertake a comprehensive desk review of all relevant documentation provided by the two local authorities and the police force, including but not limited to: budget books and financial statements; commissioning plans; service specifications; performance and demand data; previous reviews, audits, or evaluations.

- Analyse and synthesise this material to identify budget lines, governance arrangements, spend patterns, system flows and demand drivers.

4.8 Interviews and Engagement with Key Stakeholders

- Using the findings from the desk research, interviews, or other engagement activities with:

  - Finance leads from each local authority

  - Commissioning teams across children’s services, community safety, and early help

  - Police finance and operational leads

- Use these engagements to:

  - validate budget information

  - understand how money moves through the system

  - identify value leaks, duplication, and inefficiencies

  - explore opportunities for pooled budgets, joint commissioning, and structural change

  - surface barriers, risks, and governance constraints

4.8 Co-Production and Validation

- Facilitate sessions with partners to test and refine:

  - system maps

- financial flow diagrams

- crisis vs prevention spend analysis

- identified problems and opportunities

- emerging recommendations

- ensure findings are grounded in operational reality and jointly owned across agencies.

Availability of data and staff resource

The SPS Provider will be provided with access to key members of staff from within our Pilot partners, including Gateshead Local Authority, South Tyneside Council and Northumbria Police.  Relevant financial data will be made readily available for analysis. In the inception meeting the commission supplier and the pilot partnership will make a series of decisions about which wider budgets (such as health and education) are in scope.

The SPS Provider and the Relevant Authority acknowledge and agree to sign a Data Processing Agreement (DPA) directly between the Relevant Authority and the SPS Provider.

- Milestones

Combination – This contract will operate on a hybrid model incorporating both fixed fee deliverables and consumption of time and effort Day Rate (8 hours).

Specific milestone dates to be agreed between the contracting authority and successful SPS provider following contract award.

| Line Item | Description | Completion Trigger | Start Date | End Date |
| --- | --- | --- | --- | --- |
| Inception Report | Containing a project plan and setting out data requirement and key dependencies | Approval of inception report | August 2026 | August 2026 |
| Baseline Mapping | A comprehensive baseline financial map of the system Integrated system maps showing service pathways and financial flows •Analysis of value leaks, inefficiencies and cross-system impacts | Approval of baseline mapping report | August 26 | September 26 |
| Recommendation Report | Identification of opportunities for prevention, integration and resource optimisation Recommendations for structural and operational change, including governance considerations | Approval of short recommendations report | September 26 | October 26 |
| Final Report | High level report pulling headlines from previous products suitable for senior leadership | Approval of final recommendations. | October 26 | October 26 |

- Contract Management (Measuring Success and Review)

Contract Management arrangements will be carried out in line with the Services Supply Agreement (SSA) by submitting a Supplier Payment Request (SPR).

Contract variations

During project delivery it may be necessary to make changes to the SPS Provider’s contract including, but not limited to, scope of services, project milestones, end date, value, etc. Changes shall be discussed and agreed between the Contracting Authority and the SPS Provider and actioned in accordance with Bloom’s Change Control Procedure. The requested change(s) will not be considered implemented until the Change Control Notice (CCN) has been fully signed by the SPS Provider and Bloom. Delays in actioning the change(s) could cause payment issues and risk continued delivery of the project.

- Data Protection Schedule

For any personal data being shared directly between: (I) the Relevant Authority to the SPS Provider; or (II) the SPS Provider to the Relevant Authority, the Relevant Authority and SPS Provider will undertake a Data Protection Impact Assessment (DPIA) in relation to personal data being processed in this project, and where deemed appropriate enter into a separate Data Processing Agreement directly with the SPS Provider.

| No | Description | Details |
| --- | --- | --- |
| 1 | Subject Matter of the Processing | The processing of data in relation to the delivery of the Forensic Budget Mapping Commission for the Place-Based Budget Pilot, including the analysis of service activity, expenditure, demand and outcomes to support evidence-based decision making. |
| 2 | Duration of the Processing | The data will be provided for the duration of the Project covering for the provision of specialist professional services. The contract expires on the project end date at which time the information will be reviewed. |
| 3 | Nature and Purposes of the Processing | The nature of the processing includes the collection, recording, organisation, storage, retrieval, consultation, analysis and reporting of data. The purpose of the processing is to undertake forensic budget mapping, analyse expenditure and service activity across relevant public services, understand service demand and delivery patterns, and provide evidence, findings and recommendations to support the objectives of the Place-Based Budget Pilot. |
| 4 | Type of Personal Data | For the purposes of the contract, the Authority will disclose the following information directly to the SPS Provider: ​ The Authority may disclose the following information to the supplier: Aggregated service use data Aggregated financial and expenditure data Pseudonymised case-level data where necessary for analytical purposes Demographic information presented in aggregated or pseudonymised form (such as age range, gender, ethnicity and geographical area) Aggregated information relating to referrals, assessments, interventions, service utilisation and outcomes Stakeholder contact information required for project administration and engagement activities (name, organisation, job title, work email address and work telephone number) Information will be provided in aggregated, anonymised or pseudonymised form and will not include directly identifiable personal data. |
| 5 | Categories of Data Subject | Personal data relating to the Authorities staff (including temporary or agency staff) concerned with the Work Order: • Employees and representatives of the Authority and partner organisations involved in the commission • Members of governance groups, working groups and stakeholder engagement activities Aggregated (non-personal) Data may relate to: • Young people receiving, or having previously received, support from relevant services • Parents, carers or family members where reflected within aggregated datasets |
| 6 | Plan for return and destruction of the data once the processing is complete UNLESS requirement under union or member state law to preserve that type of data | The SPS Provider agrees that all data supplied will be retained no longer after the expiry or termination of the Work Order and shall be destroyed as soon as practicable. |

The SPS Provider will review the completed schedule and the Relevant Authority’s DPA or DSA template.

- Evaluation

All proposal submissions will be evaluated as follows:

Minimum and Further Requirements: Pass / Fail

Qualification: Pass/Fail

Quality: 80%

Price: 20%

Minimum and Further Requirements

Minimum Requirements: For information only, where Yes is indicated to any of the questions the Further Requirements section must be fully completed.

Further Requirements: The Authority will assess and consider the information provided in accordance with their policies. Where Yes is indicated to any of the questions the Authority may consider the bid, in accordance with PPN 01/22.

| Minimum Requirements and Further Requirements: |  |  |
| --- | --- | --- |
| Minimum Requirements |  |  |
| Business Dealings within Russia or Belarus | Are any of the following: - your Organisation, - any of its Group, Holding, Parent Companies, - your subcontractors (used to deliver the services) registered in or undertaking business in Russia or Belarus? If Yes, please provide details for consideration to enable the Authority to assess in accordance with their policies: | Yes/No |
|  | Do any of the following: - your Organisation, - any of its Group, Holding, Parent Companies, - your subcontractors (used to deliver the services) have a Person with Significant Control residing or domiciled in Russia or Belarus, or have Russia or Belarus nationality? If Yes, please provide details for consideration to enable the Authority to assess in accordance with their policies: | Yes/No |
| Further Requirements (to be fully completed ONLY if you have answered Yes to any of the Minimum Requirements questions) |  |  |
| Business Dealings within Russia or Belarus | - Is your organisation (or any member of your supply chain which you rely on to deliver the contract) registered in the UK (or in a country the UK has relevant international agreement with reciprocal rights of access to public procurement)? If Yes, please provide details for consideration to enable the Authority to assess in accordance with their policies. Note: The information you provide may include but is not limited to; your (or the supplier you will rely on to deliver the contract) UK's company registration name and company number and / or providing details of the company including but not limited to; the relevant country the company was established in. | Yes/No |
|  | - Does your organisation (or any member of your supply chain which you rely on to deliver the contract) have significant operations in the UK (or in a country the UK has relevant international agreement with reciprocal rights of access to public procurement)? If Yes, please provide details for consideration to enable the Authority to assess in accordance with their policies. Note: The information you provide may include but is not limited to; the relevant country where you (or the supplier you will rely on to deliver the contract) has significant operations and a high-level description of those substantive business* operations. *Substantive business operations mean having a registered office, factory or other permanent base in the relevant country from which meaningful business operations are being conducted. In-Scope Organisations should conduct due diligence to check supplier details with Companies House and other open information sources or seek verification directly from the supplier. | Yes/No |

| Qualification – Pass/Fail |  |  |
| --- | --- | --- |
| Qualification Area | Evaluation Criteria | Pass/Fail |
| Data Processing Agreement | The appointed SPS Provider to agree and confirm to enter into a Data Processing Agreement (DPA) with the Contracting Authority at Post Award. Yes = Pass No = Fail | Pass/Fail |

| Quality (80%) |  |  |
| --- | --- | --- |
| Quality Area | Evaluation Criteria | (%) Weighting |
| Evidence of Delivering Similar Projects | - Please provide an overview of your company and the services you deliver. - Please provide at least two relevant case studies that provide evidence of delivering similar projects including the following: - Ability to synthesise complex financial and operational data into clear insights. - Evidence of delivering similar work at pace and to a high standard. - Clear evidence of experience working in or with relevant local authority or public sector departments, including: policing, health and children services departments. - Please provide the names of 2 reference providers that can provide assurance of your capability to deliver the requirement | 25% |
| Ability to Meet the Requirements | - Please confirm that you can meet all requirements within the required timescales - Please provide a project plan that details how you would deliver the required outcome | 20% |
| Delivery Methodology for the Overall Project | - Please detail your proposed approach to delivering this project - Please provide details of your delivery assurance processes | 35% |
| Delivery Team | - Please provide CVs for your proposed delivery team | 20% |

Scoring Descriptors (Quality)

Quality will be evaluated in accordance with the Weighting and Evaluation Methodology below.

Each question has been assigned a weighting to reflect their importance. Each question is then scored on the merit of the bidder’s response, from 0 (low) to 5 (high).

| Scoring Grade | Descriptor | Numeric Score | % Score |
| --- | --- | --- | --- |
| Unacceptable | Unanswered or failed to adequately address the requirement | 0 | 0 |
| Poor | The information submitted is very limited, inconsistent with the rest of the submission, and / or no supporting documentation has been provided | 1 | 20 |
| Fair | The information submitted is limited, has some inconsistencies with the rest of the submission and / or insufficient supporting documentation has been provided. | 2 | 40 |
| Satisfactory | Satisfactory response to the requirements which provides adequate evidence but contains inconsistencies. | 3 | 60 |
| Good | Good response to the requirements which provides evidence which is clear but has minor inconsistencies. | 4 | 80 |
| Excellent | Excellent response to the requirements which provides detailed evidence which is clear, complete and consistent. | 5 | 100 |